## Planning Phase 2
Date of the test | Test Day | Test Scenario
2015-12-10 | B | Daily Auctions 08.01.2016, 16-24 Intraday Auctions
2015-12-11 | C | Daily Auctions 09.01.2016, 00-24 Intraday Auctions
2015-12-14 | B | Daily Auctions 10.01.2016, 16-24 Intraday Auctions
2015-12-15 | C | Daily Auctions 11.01.2016, 00-24 Intraday Auctions
2015-12-16 | B | Daily Auctions 11.01.2016, 16-24 Intraday Auctions
2015-12-17 | C | Daily Auctions 13.01.2016, 00-24 Intraday Auctions
2015-12-18 | D | Shadow Auctions

## Test day B details
Daily Auctions, 16-24 Intraday Auctions
# | Test Time | Partie/s Involved | Description
1 | 12:00 | JAO | Create Daily Auction
2 | 13:00-13:30 | JAO=>MPs | Publishing of Daily AS and OC
3 | 13:30-14:30 | MPs=>JAO | Bidding gate open
4 | 14:30-15:00 | JAO=>MPs | Sending of the Daily Allocation Results and CUAs (+ Min/Max AAC, if relevant)
5 | 15:00 | JAO | Create Intraday Auctions for 16-24OH
6 | 15:20-15-40 | JAO=>MPs | Publishing of Intraday AS and OC
7 | 15:40-16:40 | MPs=>JAO | Bidding gate open
8 | 16:40-17:00 | JAO=>MPs | Sending of the Intraday Allocation Results and CUAs

## Test day C details
Daily Auctions, 00-24 Intraday Auctions
# | Test Time | Partie/s Involved | Description
1 | 12:00 | JAO | Create Daily Auction
2 | 13:00-13:30 | JAO=>MPs | Publishing of Daily AS and OC
3 | 13:30-14:30 | MPs=>JAO | Bidding gate open
4 | 14:30-15:00 | JAO=>MPs | Sending of the Daily Allocation Results and daily CUAs (+ Min/Max AAC, if relevant)
5 | 15:00 | JAO | Create Intraday Auctions for 1-24OH
6 | 15:20-15-40 | JAO=>MPs | Publishing of Intraday AS and OC
7 | 15:40-16:40 | MPs=>JAO | Bidding gate open
8 | 16:40-17:00 | JAO=>MPs | Sending of the Intraday Allocation Results and intraday CUAs

## Test day D details
Daily Auctions, Intraday Auctions
# | Test Time | Partie/s Involved | Description
1 | 12:00 | JAO | Create Shadow Auction as fallback to Daily Auction
2 | 13:30-14:30 | MPs=>JAO | Default bids submitted for shadow auctions as fallback to Daily Auction
3 | 14:30-15:00 | JAO=>MPs | Sending of the Shadow Daily Allocation Results and CUAs
4 | 15:00 | JAO | Create Shadow Auction as fallback to Market Coupling
5 | 15:40-16:40 | MPs=>JAO | Bidding gate open
6 | 16:40-17:00 | JAO=>MPs | Sending of the Shadow Allocation Results and CUAs