## Planning Phase 2
Date of the test | Test Day | Test Scenario
2015-12-22 | E | Daily Auction 19.01.2016, 00-24 Intraday Auctions 19.01.2016, 16-24 Intraday Auctions 18.01.2016, Shadow Auctions 19.01.2016
2015-12-23 | E | Daily Auction 20.01.2016, 00-24 Intraday Auctions 20.01.2016, 16-24 Intraday Auctions 19.01.2016, Shadow Auctions 20.01.2016
2015-12-24 | E | Daily Auction 21.01.2016, 00-24 Intraday Auctions 21.01.2016, 16-24 Intraday Auctions 20.01.2016, Shadow Auctions 21.01.2016
2015-12-25 | F | Fallback Daily Auction 22.01.2016, 00-24 Intraday Auctions 22.01.2016, 16-24 Intraday Auctions 21.01.2016, Shadow Auctions 22.01.2016
2015-12-26 | E | Daily Auction 23.01.2016, 00-24 Intraday Auctions 23.01.2016, 16-24 Intraday Auctions 22.01.2016, Shadow Auctions 23.01.2016
2015-12-27 | E | Daily Auction 24.01.2016, 00-24 Intraday Auctions 24.01.2016, 16-24 Intraday Auctions 23.01.2016, Shadow Auctions 24.01.2016
2015-12-28 | F | Fallback Daily Auction 25.01.2016, 00-24 Intraday Auctions 25.01.2016, 16-24 Intraday Auctions 24.01.2016, Shadow Auctions 25.01.2016
2015-12-29 | E | Daily Auction 26.01.2016, 00-24 Intraday Auctions 26.01.2016, 16-24 Intraday Auctions 25.01.2016, Shadow Auctions 26.01.2016
2015-12-30 | E | Daily Auction 27.01.2016, 00-24 Intraday Auctions 27.01.2016, 16-24 Intraday Auctions 26.01.2016, Shadow Auctions 27.01.2016

## Test day E details
Daily Auctions, Intraday Auctions, Shadow Auctions
# | Test Time | Partie/s Involved | Description
1 | 12:00 | JAO | Create Daily Auction
2 | 13:00-13:30 | JAO=>MPs | Publishing of Daily AS and OC
3 | 13:30-14:30 | MPs=>JAO | Bidding gate open
4 | 14:30-15:00 | JAO=>MPs | Sending of the Daily Allocation Results and CUAs (+ Min/Max AAC, if relevant)
5 | 15:00 | JAO | Create Intraday Auctions for 16-24, Create Intraday Auctions for 1-24
6 | 15:20-15:40 | JAO=>MPs | Publishing of Intraday AS and OC
7 | 15:40-16:15 | JAO | Run Shadow Auctions*
8 | 15:40-16:15 | MPs=>JAO | Bidding gate open
9 | 16:15-16:30 | JAO=>MPs | Sending of the Intraday and Shadow Allocation Results and CUAs
* Bids for Shadow Auctions are default bids to be placed before 15:40

## Test day F details
Daily Auctions, Intraday Auctions, Shadow Auctions
# | Test Time | Partie/s Involved | Description
1 | 12:00 | JAO | Create Daily Auction
2 | 13:00-13:30 | JAO=>MPs | Publishing of Daily AS and OC
3 | 13:30-14:00 | MPs=>JAO | Bidding gate open
4 | 14:00-14:30 | JAO | Daily Auction cancelled
5 | 14:30-15:00 | JAO=>MPs | Sending of the Fallback Daily Allocation Results and CUAs (+ Min/Max AAC, if relevant)*
6 | 15:00 | JAO | Create Intraday Auctions for 16-24, Create Intraday Auctions for 1-24
7 | 15:20-15:40 | JAO=>MPs | Publishing of Intraday AS and OC
8 | 15:40-16:15 | JAO | Run Shadow Auctions**
9 | 15:40-16:15 | MPs=>JAO | Bidding gate open
10 | 16:15-16:30 | JAO=>MPs | Sending of the Intraday and Shadow Allocation Results and CUAs
* Bids for Fallback Daily Auctions are default bids to be placed before 14:00
** Bids for Shadow Auctions are default bids to be placed before 15:40