## Slide 1: CWE Consultative Group meeting Brussels, April 17th 2019 Sheraton Brussels Airport

## Slide 2: 6.CWE Flow-Based Intraday developments FB IDCC implementation: introduction (1/2)
  CWE TSOs started to work on new Intraday capacity calculation methodologies in Q2 2014. The focus was on implementing an coordinated ID ATC increase/decrease process after FBMC prior to developing an Intraday flow-based capacity calculation (the target solution).
  In Q2 of 2015 the work for Flow Based Intraday Capacity Calculation was initiated (FB IDCC) while improving the ID ATC increase/decrease process in parallel.
  Accomplishments for CWE Intraday ATC after FBMC
  Go-live of the coordinated ID ATC after FBMC (increase/decrease process) in Q1 2016 and implementation of further improvements
    Update of maximum increase values and partial steps in May 2017
    Daily publication of increase/decrease values in September 2017
Accomplishments for CWE Flow based IDCC can be found on the next slide

## Slide 3: 6.CWE Flow-Based Intraday developments FB IDCC implementation: introduction (2/2)
  Accomplishments for Flow Based IDCC
  Q1 2015: NRA position paper on FB DA methodology
    Calls for development of ID capacity re-calculation methodology, based on latest available information
  Q3 2016: FB IDCC initial experimentation
  Q2 2017: FB IDCC methodology submitted to NRAs including one recomputation of ID ATCs
  Q2 2017 – Q3 2018: Internal // run (using new prototypes including Remedial Action Optimization) performed by CWE TSOs.
  Q3 2017: FB IDCC methodology approved by some NRAs (but an update is requested before the go-live).
  Q2 2018: Amended FB IDCC methodology submitted considering NRAs’ position paper (Q3 2017)

## Slide 4: 6.CWE Flow-Based Intraday developments FB IDCC implementation: current status and next steps
Since the beginning, CWE FB IDCC was designed to use the new CGMES standards format defined by ENTSO-E. Despite some mitigation measures, the CWE FB IDCC project as today cannot continue as initially planned due to the high risks and uncertainties, and the unavailability of a pan-European CGM creation process in CGMES.
CWE TSOs and NRAs have extensively discussed the way forward with FB IDCC, considering the delay in implementation of the CGMES standards, and agreed to put on hold FB IDCC activities within CWE until the CGMES transition is nearly completed.
  Implementation of CGMES standards in TSOs exchanges is a prerequisite for an optimal FB IDCC solution.
  As the CGMES project has a delay of 2 years, CWE TSOs and NRAs conclude that the optimal way forward in matters of costs and time is to wait until the CGMES transition is nearly completed.
    Once the CGMES transition is near to final, a decision can be reached on whether FB IDCC developments should be continued in CWE or in the CCR Core.
CWE TSOs are assessing further improvements for the ID ATC after FBMC increase/decrease process (see next topic).